## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Btn setup | 1 | 1 | 1 | 2022-03-10 |  | M | Mitigated, I didn't solve the laser button yet
Slider setup | 1 | 1 | 1 | 2022-03-10 |  | R | Resolved
Timer setup | 1 | 1 | 1 | 2022-03-10 |  | R | Resolved
ITC setup | 1 | 1 | 1 | 2022-03-10 |  | R | Resolved
slider monitor | 1 | 1 | 1 | 2022-03-10 |  | R | Resolved
Physics task | 1 | 1 | 1 | 2022-03-10 |  | M | Done
lcd task | 1 | 1 | 1 | 2022-03-10 |  | M | Done
led task | 40 | 13 | 520 | 2022-03-10 |  | M | Neally finish it, but not that perfect due to timer issue
slider operator | 1 | 1 | 1 | 2022-03-10 |  | R | Resolved
shield task | 1 | 1 | 1 | 2022-03-10 |  | R | Resolved
Data structure setup | 1 | 1 | 1 | 2022-03-15 |  | R | Resolved
Bounce from the wall | 1 | 1 | 1 | 2022-03-15 |  | R | resolved when I was doing physics task
Ball position calculation | 1 | 1 | 1 | 2022-03-15 |  | R | Resolved by getting help from Jon
platform position calulation | 1 | 1 | 1 | 2022-03-15 |  | R | Resolved by getting help from Jon
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100