## Sheet1
Task | Estimate | Actual | In progress | Status | Risks
Btn setup | 2 hrs | 4hr/4hr | Done | Complete | low | Both button have been done
Slider setup | 3 hrs | 2hr | Done | Complete | low | Done | Mainly about the laser and boost function
Timer setup | 2 hrs | 1hr | Done | complete | low | Done | New Timers can be added whenever I need more
ITC setup | 3hr | 1hr | Done | complete | low | Done | New ITCs can be added whenever I need more
slider monitor | 10hr | 2hr | Done | Complete | mid | Done | Record the position of platform
Physics task | 10hr | 6hr | Done | Complete | Mid | Done | Position calculation is the most difficult part in this Task
lcd task | 5hr | 4hr/4hr | Done | Complete | Mid | Done | More debugging information jave been added
led task | 2 hrs | 3/hr/2hr | 99% Complete | 99% Complete | low | Couldn't finish because the result of calculation are not what I expect to see. Most of time, it's nearly a zero.
slider operator | 5hr | 3hr | Done | Complete | High | Done | Some hardware issue still exist due to timer issue
shield task | 5hr | 2hr/4hr | Done | Complete | High | Done | Mainly about the laser and boost function
| 47hr | 28